## Dashboard
ID | Task Name | Subtask | Estimated Date | Estimated Time | Actual Date | Actual Time | Additional Information | Status | Resource
1 | Creating remote registory | Create a repository | 17/09/21 | 1 | 17/09/21 | 0.5 | repo name: basic_channel | Done | Navodika
|  | Create a project and automate | 17/09/22 | 1 | 17/09/21 | 0.5 | project name: tranceiver Columns: Backlog, Todo, Ongoing, Done | Done | Navodika
| Create basic channel | Generating bit stream | 17/09/23 | 1 | 17/09/22 | 0.5 | Data rate : 1 bps | Done | Navodika
|  | Implement polar line coding | 17/09/24 | 1 | 17/09/23 | 0.5 | Bipolar nrz | Done | Navodika
|  | BPSK modulator | 17/09/25 | 2 | 17/09/24 | 3 | Need S/P | Done | Navodika
|  | AWGN channel | 17/09/26 |  |  |  |  | Todo | Navodika
|  | Coherent detection | 17/09/27 |  |  |  |  | Todo | Navodika
|  | Binary ditector | 17/09/28

## Variables
Status | Resource
Todo | Navodika
Ongoing
Done